## AutoReferee
ID | Event | Caused by (Cause) | Results in (Effect) | Description of Event | Probability | Consequence | Severity | _VAL | Response | Mitigation | Contingency
1 | Performance Problem for The Survillance Cameras | Communication Loss, Communication Speed on Router | Defficient View Angle | The survillance cameras may not be able to change their view angle and focus distance. | 4 | 2 | 8
2 | Recognition Speed Performance | Inefficient Coding | Time Delay | AutoReferee system may be faced with time delay due to implemented software. | 3 | 4 | 12
3 | Communication Problem with Hardware | Object Detection Problem, Sensor Resolution | Rough Estimation, Communication Problem | AutoReferee system may be faced with communication loss about data systems. | 4 | 3 | 12
4 | Data Creating Problem | Data Structure Problem, Sensor Problem | Complete or Partial Data Defficiency | Turtles may not be able to create the data of the game. | 2 | 5 | 10
5 | Noise Problem on Data | Sensor Resolution, Sensor Range, Environmental Problem | Complete or Partial Recognition Loss | The transferred data may not be able to be use in the decision-making algorithm. | 3 | 4 | 12
6 | Tech United Team Calendar | Time Management, Covid-19, Hardware Problem | Meager or No Data Set | Tech United team may not offer to simulate the real game. | 2 | 5 | 10
7 | Survillance Camera Communication Problem | Knowledge Defficiency, Communication Speed on Router | Partial or No Record | The survillance cameras may not be able to record the game. | 4 | 3 | 12
8 | Hardware Sensor Problem | Sensor Trouble, Sensor Range, Environmental Problem | Meager or No Data Set | Turtles may not be able to get data from its sensor systems. | 2 | 4 | 8
9 | Software Sufficiency | Inefficient Library | Partial Solution and/or Performance Problem | The Matlab may not be able to offer necessary libraries to create functions or the brute force may be required in development stage. | 1 | 3 | 3
10 | Environmental Dynamics | Peak in Ball Velocity | Rough Estimation, Detection Problem | AutoReferee system may be faced with position detection during high velocity | 3 | 4 | 12
0
0
0
0
0
0
0

## Risks
ID | Event | Caused by (Cause) | Results in (Effect) | Description of Event | L | I | _ENC | _VAL | Response | Mitigation | Contingency
2 | Team is not allowed to change the position of the stationary cameras to record the match
3 | Tech United expert not available to simulate the real game
4 | Data is too noisy to use in the decision-making algorithm
5 | TURTLES not able to create the data of the game
Surveillance cameras not working to record the game

## Risk Posture
L | I | _ID | Posture |  | Posture Value | Risk Reponse
0 | 0 | 0 | Resolved | Negligible | Resolved | Identified
1 | 1 | 11 | Acceptable | Minimal | Acceptable | No response required
1 | 2 | 12 | Acceptable | Minor | Tolerable | Planned
1 | 3 | 13 | Tolerable | Moderate | Undesirable | Implemented
1 | 4 | 14 | Undesirable | Major | Unacceptable | Expired
1 | 5 | 15 | Acceptable | Severe | X
2 | 1 | 21 | Acceptable
2 | 2 | 22 | Acceptable
2 | 3 | 23 | Tolerable
2 | 4 | 24 | Undesirable
2 | 5 | 25 | Acceptable
3 | 1 | 31 | Acceptable
3 | 2 | 32 | Tolerable
3 | 3 | 33 | Undesirable
3 | 4 | 34 | Undesirable
3 | 5 | 35 | Acceptable
4 | 1 | 41 | Tolerable
4 | 2 | 42 | Undesirable
4 | 3 | 43 | Undesirable
4 | 4 | 44 | Unacceptable
4 | 5 | 45 | Tolerable
5 | 1 | 51 | Undesirable
5 | 2 | 52 | Undesirable
5 | 3 | 53 | Unacceptable
5 | 4 | 54 | Unacceptable
5 | 5 | 55 | Unacceptable
1 | 75 | 85 | X

## Sheet3
Week | Acceptable | Tolerable | Undesirable | Unacceptable
1 | 2 | 1 | 4 | 5
2 | 3 | 2 | 6 | 8
3 | 5 | 1 | 5 | 7
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42